## Summary
QA Execution Report — Admission / Installment / Edit / Cancellation / Bulk Upload / Refund
App | Shri Ji Fee Management Workflow System
Environment | Testing (https://shriji-fee-develop.webmobsoft.com), Main Centre, session 2026-27
Execution Date | 2026-08-04
Executed By | Claude (QA Automation), via Playwright MCP live browser execution
Test Case Source | shriji-fee-admission-installment-e2e-test-cases.xlsx (sheet "Test Cases")
Roles Used | Staff (ashish1660webmob@gmail.com) and Admin (ashishwebmob1990@gmail.com)
1. Executive Summary
Every test case in the sheet (TS_101-TS_126, 26 total) was executed sequentially against the live testing environment this run. No test case was skipped or blocked - full credential and environment access was available throughout.
Status | Count | Test Case IDs
Done | 24 | TS_101-TS_105, TS_107-TS_125 (excluding 106, 126)
Issue | 2 | TS_106, TS_126
Blocked | 0 | -
Skipped | 0 | -
Pass rate: 24/26 (92%). Both Issues are documented in the Findings/Bugs sheet with full reproduction steps and are tracked as BUG-001 and BUG-002.
2. Scope Covered
• Admissions: create (partial/full payment), search, edit (Admin), cancel (Admin, with/without refund), role-based Actions visibility (Staff vs Admin), field validation.
• Installments: record payment, view transaction history, Actions-menu state (ongoing vs fully-paid), data integrity (Total Paid / Pending Amount reconciliation).
• Bulk Upload: template download/structure, valid upload, invalid file type, mixed valid+invalid rows, duplicate Admission No. rejection, nonexistent-Course rejection.
• Refund flow: toggle behavior, max-refundable validation, partial refund execution, transaction ledger correctness, and re-verification of a previously known defect (no-refund mislabeling).

## Findings - Bugs
Field | BUG-001 | BUG-002
Bug ID | BUG-001 | BUG-002
Issue Summary | False "Reissue receipt?" prompt on a name-only edit (New) | "Refunded" status/count shown even when no refund was requested (Confirmed, pre-existing)
Test Case | TS_106 | TS_126
Module / Feature | Admissions / Edit Admission (Admin) | Admissions + Installments / Cancel Admission, no-refund path
Severity | Medium | Medium
Priority | Medium | Medium
Status | Open | Open (re-verified)
Steps to Reproduce | Admin -> Edit any Confirmed admission -> change ONLY the Name field (leave every fee/deposit field untouched) -> click "Update Admission" | Admin -> cancel a Confirmed admission with Total Paid > 0, leaving "Initiate Refund" OFF -> open that record's Installments -> "View All Transactions"
Expected Result | "Admission updated" toast fires directly; no extra confirmation, since no fee/deposit field changed | STATUS reads "Cancelled" (matching the Installments list row); REFUNDED stat card unaffected
Actual Result | A modal appears: "Reissue receipt? You've changed a fee or deposit detail. Saving will void the current receipt and issue a new one with a new receipt number." - factually incorrect for a name-only change. Clicking through still saves correctly (name updates, toast fires). | STATUS reads "Refunded" (REFUNDED AMOUNT correctly Rs.0.00, but the status word is wrong); the Installments page REFUNDED stat card increments by the count of paid installment rows on that admission
Root Cause (unconfirmed) | The fee/deposit-change detection likely fires on any form submission rather than diffing which field actually changed | Status/stat derivation likely keys off "Cancelled + has prior paid installments" rather than an actual refund-initiated flag
Screenshot | screenshots/2026-08-04/TS_106_ISSUE_FalseReissueReceiptPrompt.png | screenshots/2026-08-04/TS_126_ISSUE_RefundedStatusBugWithZeroAmount.png
Impact / Additional Notes | Non-blocking (edit still completes correctly), but misleading wording risks confusing Admins into thinking a receipt will be voided when editing plain contact details | Any reporting/reconciliation built on the "Refunded" label or REFUNDED stat card will overcount real refunds. This is a re-verification, not a new find - first surfaced earlier the same day; confirmed still present. Recommend keeping in the regression suite until fixed.

## Non-Defect Observations
Test Case | Observation
TS_113 | The disabled "Submit Admission" button retains its normal blue styling rather than a visually "greyed-out" disabled look. Confirmed functionally disabled via the DOM ([disabled] attribute present) - purely a cosmetic inconsistency, not filed as a defect.
TS_121 | Previously flagged in the test-case document as untested / "no automation candidate." Executed this run - the app correctly rejects a bulk-import row referencing a Course that doesn't exist at the centre, with a clear, specific error message. Recommend updating that test case's Automation Candidate flag to "Yes" going forward.

## Test Data - Validation
5. Test Data Used
All records created this run use the TCX_1xx/TCX_12x synthetic naming convention (e.g. TCX_101, TCX_106, TCX_107, TCX_117, TCX_119A/B, TCX_121, TCX_122) plus bulk-upload files under .playwright-mcp/bulk-upload-tests-run2/. No real user or financial data was used. Two records (TCX_107, TCX_122) were intentionally cancelled as part of TS_107/TS_110/TS_115/TS_122-126; these cancellations are expected, reversible-in-intent test actions, not accidental data loss.
6. Validation Checklist
☑ | Every test case (26/26) has been executed.
☑ | Every row has an execution status (Done/Issue - no blanks).
☑ | Every Issue-status test case has an attached screenshot.
☑ | Every Issue includes a complete bug description (Bug Reports sheet, BUG-001/BUG-002).
☑ | No test case left blank in the updated sheet.
☑ | Updated Test Cases sheet is complete and ready for sharing (new columns: Execution Status, Execution Date, Executed By, Actual Result, Bug ID, Screenshot Reference, Execution Notes - existing columns untouched).
7. Artifacts
• | shriji-fee-admission-installment-e2e-test-cases.xlsx - updated "Test Cases" sheet + new "Bug Reports" sheet
• | screenshots/2026-08-04/ - 8 evidence screenshots (TS_105/114, TS_106, TS_108, TS_113, TS_121, TS_123, TS_125, TS_126)