## Bug Report
Bug ID | Module/Page | Feature | Severity | Priority | Environment | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Evidence | Status | Reported By | Timestamp
BUG-001 | Authentication / Login | Staff login - centre assignment | High | P2 | Chromium, Windows, https://shriji-fee-testing.webmobsoft.com/login | Staff test account ashish1660webmob+13@gmail.com exists and is used for staff-role testing throughout this project. | 1. Go to /login. 2. Select Centre = 'Main Centre'. 3. Enter email ashish1660webmob+13@gmail.com and correct password. 4. Click 'Sign In'. 5. Observe error. 6. Change Centre to 'Sub Centre' (same credentials, no other change). 7. Click 'Sign In' again. | Staff account should successfully authenticate against whichever centre it is actually assigned to, and land on /dashboard. | Both attempts fail with the identical alert: "Your account is not assigned to this centre. Please select your centre and try again." The account cannot log in under either of the only two centres that exist in this environment (Main Centre, Sub Centre) - there is no third option to try. This fully explains the persistent staff-login failures observed throughout the automated Playwright suite (Phase 1 and Phase 2), which had been treated as an unexplained external blocker until now. IMPORTANT ADDITIONAL FINDING: checking Users Management (/users) shows this exact email does NOT appear anywhere in the user list, while a DIFFERENT, genuinely active staff account exists: 'Satff user1' <ashishwebmob1990@gmail.com>, role=staff, status=active. This strongly suggests the project's configured staff test credential (STAFF_EMAIL in .env, used throughout the automated Playwright framework) is simply the wrong/stale account, not a real centre-assignment defect - the actually-provisioned staff account is a different email entirely. Recommend the QA/dev team confirm the correct staff credential and update .env accordingly. |  | New | Claude AI | 2026-07-09 11:12:59
BUG-002 | Authentication / Login & Forgot Password | Field validation message consistency | Low | P4 | Chromium, Windows, https://shriji-fee-testing.webmobsoft.com/login and /forgot-password | None. | 1. Go to /login, leave Email empty, submit -> note error text under the field. 2. Go to /forgot-password, leave Email empty, submit -> note error text under the field. 3. Compare the two email input placeholders and the two error messages. | Consistent placeholder text and consistent validation wording for the same logical field (email) across pages of the same app. | Login page email placeholder is "you@company.com" and its empty/invalid-email error is "Enter a valid email". Forgot Password page email placeholder is "you@shriji.com" and its empty/invalid-email error is "Enter a valid email address". Also, both pages show the same wording for a genuinely empty field as for a malformed one ("Enter a valid email[...]"), which is slightly misleading copy for the empty-field case. |  | New | Claude AI | 2026-07-09 11:12:59
BUG-003 | Authentication / Login | Console error logging on expected/handled failures | Low | P4 | Chromium, Windows, https://shriji-fee-testing.webmobsoft.com/login | None. | 1. Go to /login and submit valid centre/email with a wrong password. 2. Open browser console. 3. Separately: while logged out, navigate directly to /dashboard by URL and open the console. | Expected, user-facing, already-handled failure conditions (wrong password -> shown as an inline alert; unauthenticated silent-refresh attempt before redirecting to /login) should not also be logged to the console as console.error - that channel should be reserved for genuinely unexpected failures. | Both cases log real console.error() entries ("Failed to load resource: ... 401", "[ERROR] [API] API Error 401", "[ERROR] [QueryClient] Mutation error AxiosError: Request failed with status code 401") even though the UI already handles the condition correctly. This adds noise to the console and would cause any CI check that fails a build on console.error output to false-positive on completely normal user flows (wrong password, session expiry). |  | New | Claude AI | 2026-07-09 11:12:59
BUG-004 | Admission / Add New Admission (and Edit Admission) | Mobile / Father's Mobile field validation | High | P2 | Chromium, Windows, https://shriji-fee-testing.webmobsoft.com/admissions/new | Logged in as admin. | 1. Go to Admission > Add New Admission. 2. Fill all required fields with valid data EXCEPT type 'abcdefghij' (10 letters, no digits) into the Mobile field. 3. Fill Father's Mobile with a real 10-digit number. 4. Observe the Mobile field's validation state clears once exactly 10 characters are present. 5. Click 'Submit Admission'. | Mobile and Father's Mobile should be validated as actual numeric phone numbers (10 digits, digits only) both client-side and server-side; a value like 'abcdefghij' should be rejected with an error and the record should not be saved. | The client-side validation only checks string length (exactly 10 characters) and does not check that the characters are digits - the invalid-state indicator and 'Enter 10-digit mobile number' error disappear once 10 characters of any kind are entered. The form submits successfully and the record is saved to the backend with Mobile = 'abcdefghij' (confirmed: admission PW-ADM-QAE2E5981 was created and appeared in the Admissions list with status 'Confirmed'). This is a genuine end-to-end data-integrity gap - the backend enforces no numeric-mobile validation either. The same unvalidated Mobile field is also editable (not locked) on the Edit Admission form, so the corrupted value can persist and be re-edited indefinitely. |  | New | Claude AI | 2026-07-09 11:45:00
BUG-005 | Admission / Add New Admission | Numeric field default state (Fees Paid, Final Fees) | Medium | P3 | Chromium, Windows, https://shriji-fee-testing.webmobsoft.com/admissions/new | None. | 1. Go to Admission > Add New Admission. 2. Immediately open the browser console (before interacting with the form). | No console warnings on a fresh page load with no user interaction. | Two identical console warnings fire immediately on page load: "The specified value 'NaN' cannot be parsed, or is out of range." This points to the 'Fees Paid' and 'Final Fees' numeric spinbuttons being initialized with an uncontrolled/NaN internal value before the user types anything, rather than an empty string or 0. The same pattern reproduces on the Add New Installment form (/installments/new) - clicking 'Reset' there fires the identical warning 3 times, suggesting the same numeric-field pattern is reused across Final Fee/Remaining Fee/Fees. |  | New | Claude AI | 2026-07-09 11:45:00
BUG-006 | Admission / Add New Admission (Class / Course dropdown) | Course master-data quality | Medium | P3 | Chromium, Windows, https://shriji-fee-testing.webmobsoft.com/admissions/new | None - the dirty data is already present in the shared testing environment's Course master list. | 1. Go to Admission > Add New Admission. 2. Click the 'Class / Course' dropdown. | Only real, intentional course names should appear in the dropdown. | The dropdown's first option is a junk/garbage entry: "12333333)))((((&&&&&##@@!!" - clearly test data that was entered into the Course master list (Settings) and never cleaned up. Any user creating a new admission sees this nonsensical option at the top of the list. Not an application code defect, but a real, currently-visible data-quality/UX issue in the shared testing environment. |  | New | Claude AI | 2026-07-09 11:45:00
BUG-007 | Installments / Add New Installment | Fees field zero-value validation | Medium | P3 | Chromium, Windows, https://shriji-fee-testing.webmobsoft.com/installments/new | Logged in as admin. An admission with a non-zero remaining balance exists (used PW-ADM-MRC3TKO34AK, Remaining Fee ₹22,000). | 1. Go to Installments > Add New Installment. 2. Enter the Admission Number and let the rest auto-fill. 3. Select Payment Method = Cash. 4. Type '0' into the Fees field. 5. Observe the field's validation state and the Submit Installment button. | A ₹0 installment payment is not a meaningful business record and should be rejected with a validation error (e.g. 'Fees must be greater than 0'), consistent with the Admission form's own 'Must be greater than 0' rule for its Fees Paid field. | Entering 0 shows no invalid state and no error message, and the 'Submit Installment' button becomes enabled (not disabled) - the same field correctly blocks values ABOVE the remaining balance ('Fees cannot exceed the remaining fee') but does not block 0. Not submitted to avoid creating a meaningless ₹0 test record, but the enabled Submit button is sufficient evidence the client-side gate would allow it through. |  | New | Claude AI | 2026-07-09 12:05:00
BUG-008 | Users Management | User name data quality | Low | P4 | Chromium, Windows, https://shriji-fee-testing.webmobsoft.com/users | None - visible immediately on the Users Management list. | 1. Go to Users Management (/users). 2. Look at the first row's Name column. | User display names should be free of typos. | A real, currently-active staff user is named "Satff user1" (should be "Staff user1") - a typo entered at account-creation time. Likely user-entered data rather than an app defect, but it is currently visible to any admin viewing this list. |  | New | Claude AI | 2026-07-09 12:15:00
BUG-009 | Settings / Change Password | Password field autocomplete attributes | Low | P4 | Chromium, Windows, https://shriji-fee-testing.webmobsoft.com/settings | None. | 1. Go to Settings. 2. Open the browser console. 3. Look at the Change Password section (Current/New/Confirm New Password fields). | Password inputs should declare appropriate autocomplete attributes so browsers and password managers can offer autofill/save-password prompts correctly. | Chrome logs 3 DOM advisory messages: "Input elements should have autocomplete attributes (suggested: 'current-password')" and twice for "new-password". The Current/New/Confirm Password fields have no autocomplete attribute set. |  | New | Claude AI | 2026-07-09 12:20:00
BUG-010 | Settings / Change Password | Validation message grammar | Low | P4 | Chromium, Windows, https://shriji-fee-testing.webmobsoft.com/settings | None. | 1. Go to Settings > Change Password. 2. Type different values into New Password and Confirm New Password. 3. Click 'Change Password'. | Grammatically correct validation copy. | The mismatch error reads "Password do not match" - missing the plural 's' (should read "Passwords do not match"). |  | New | Claude AI | 2026-07-09 12:25:00