## Change Requests
CR ID | Client Ref # | Module/Page | Change Title | Description | Current Behavior | Requested Behavior | Priority | Clarification Needed | Status | Requested By | Date Logged
CR-001 | 1 | Global - Admissions, Installments, Reports, Students (Search) | Search should use Admission Number | All search operations across the app should be performed using the Admission Number. | Confirmed live (2026-07-09): search inputs on Admissions, Installments, Students and Reports all use the placeholder "Search by name or roll no..." and match only on student name or roll number. Confirmed via direct network inspection that searching by Admission Number currently returns zero results (total: 0) - the backend search endpoint does not index the admissionNo field at all. | Search endpoints/UI should match on Admission Number (in addition to or instead of name/roll no, to be confirmed with client). | High | Confirm whether Admission Number should REPLACE name/roll-no search, or be ADDED as another matchable field alongside them. | New | Client | 2026-07-10
CR-002 | 2 | Reports | Display Admission Number in report tabs | The Admission Number should be displayed in all relevant report tabs. | Confirmed live (2026-07-09): the Fee Report table's columns are Sr No, Roll, Name, Father Name, Class, Fees (₹), Payment Method, CGST, SGST, Receipt No, DD No, DD-Dated, F Year. There is no Admission Number column anywhere in Reports currently. | Add an Admission No. column to Fee Report (and any other report tab that lists per-admission/per-transaction rows). | Medium | Confirm exact column position (e.g. next to Roll No.) and whether this also applies to the GST Report's monthly summary table (which has no per-admission rows to begin with). | New | Client | 2026-07-10
CR-003 | 3a | Reports - Fee Report | Add separate tabs within Fee Report | Add separate tabs within the Fee Report section (currently a single flat table). | Confirmed live (2026-07-09): Fee Report renders as one continuous table with no internal tab navigation. | Break Fee Report into multiple tabs. | Medium | Confirm the grouping criteria for the new tabs (e.g. by course/class, by payment status, by session/year, by centre) - not specified by client yet. | New | Client | 2026-07-10
CR-004 | 3b | Reports - Fee Report | Add Date Filter (From / To) | Implement a date filter with From and To date selection on the Fee Report. | The reports service layer already accepts "from"/"to" query parameters (confirmed via source read), but no date-range filter UI is currently wired up on the Fee Report page. | Add From/To date pickers that filter the Fee Report table by date range. | Medium | Confirm which date field the filter should apply to (Deposit Date vs. DD-Dated). | New | Client | 2026-07-10
CR-005 | 4 | Admission - Add New Admission | Installment Cycle should show month names | Update the Installment Cycle field to display month names (e.g. January, February, March...) instead of the current format. | Confirmed live (2026-07-09): the Installment Cycle dropdown currently lists numeric duration options - "1 Month", "2 Months", "3 Months" ... up to "12 Months" - representing how many months apart each installment is due, not a calendar month. | Show calendar month names (January-December) in this field. | Medium | IMPORTANT - flagging for client confirmation before implementation: "Installment Cycle" is currently a duration/frequency value (how many months between installments), used to calculate each installment's due date. Calendar month names (January...December) represent a completely different concept (a specific point in the calendar, not a recurring interval). Please confirm which of these the client actually wants: (a) keep it as a duration field but relabel the options (e.g. "Monthly", "Bi-Monthly", "Quarterly" instead of "1 Month", "2 Months"), or (b) add a genuinely new field, separate from the cycle length, such as a "Start Month" picker. Implementing this literally (replacing 1-12 Months with January-December) would break the existing due-date calculation logic. | New - Needs Clarification | Client | 2026-07-10
CR-006 | 5 | Admission - Cancellation | Show correct status for Refunded vs Non-Refunded cancellations | Display the appropriate status for both Refunded and Non-Refunded cancelled admissions. | Confirmed in earlier QA session: cancelled admissions already store refundInitiated and refundAmount fields, and the Installments list does show a distinct "Refunded" status badge when a refund was issued on that installment. However, the Admissions list's own Status column only ever shows "Cancelled" regardless of refund state - there is currently no visual distinction there between a refunded cancellation and a non-refunded one. | Admissions list (and anywhere else a cancelled admission's status is shown) should distinguish Refunded vs Not Refunded, not just "Cancelled". | Medium | Confirm desired wording/badges, e.g. "Cancelled - Refunded" / "Cancelled - Not Refunded", or two separate status colors. | New | Client | 2026-07-10
CR-007 | 6a | Admission / Installments - Bulk Upload | Add missing dropdowns in Bulk Upload tabs | Add the missing dropdowns in the affected Bulk Upload tabs. | Not yet re-verified in this pass against the current build. | Add the dropdown fields the client has identified as missing. | Medium | Client has not specified which fields/tabs are missing dropdowns - needs a follow-up with the client (or a screen-recording/screenshot from them) to identify the exact fields before this can be scoped or verified against the current build. | New - Needs Clarification | Client | 2026-07-10
CR-008 | 6b | Admission / Installments - Bulk Upload | Replace Status field with Session dropdown | Replace the Status field with a Session dropdown wherever applicable in Bulk Upload. | Not yet re-verified in this pass against the current build. | Remove/replace the Status field with a Session selector dropdown in the relevant Bulk Upload tab(s). | Medium | Confirm exactly which tab(s)/template(s) this applies to, and whether Session should be a required field with a default value. | New - Needs Clarification | Client | 2026-07-10
CR-009 | 7 | Reports | Display Next Due Date in reports | Display the Next Due Date in the relevant report(s). | Not yet verified against the current build - to be confirmed which report(s) currently omit a Next Due Date column. | Add a Next Due Date column to the relevant report(s) (e.g. Fee Report / Installments Report) showing the next upcoming installment due date for each student/admission. | Medium | Confirm which specific report(s) should show Next Due Date, and the exact column position. | New - Needs Clarification | Client | 2026-07-13
CR-010 | 8 | Receipt | Add "Shri Ji" text to receipt | Add the text "Shri Ji" to the receipt. | Not yet verified against the current build - to be confirmed where on the receipt the text currently appears or is absent. | Display "Shri Ji" text on the receipt (e.g. as part of the header/institute name area). | Low | Confirm exact placement/formatting of "Shri Ji" on the receipt (header, footer, alongside institute name, etc.) and whether it replaces or supplements existing receipt text. | New | Client | 2026-07-13
CR-011 | 9 | Global | Replace "Kota" with "Kurukshetra" throughout the application | Replace "Kota" with "Kurukshetra" throughout the application wherever applicable. | Not yet verified against the current build - to be confirmed which screens/fields currently display "Kota" (e.g. address fields, dropdown options, static labels, receipts, reports). | Replace "Kota" with "Kurukshetra" in all applicable UI text, dropdown options, static labels, and generated documents (receipts/reports). | High | Confirm the full list of locations where "Kota" appears (UI labels vs. stored/historical data vs. dropdown option values) so this only updates labels/options and does not unintentionally alter historical records. | New - Needs Clarification | Client | 2026-07-13
CR-012 | 10 | Global - Search | Update Search Functionality per latest client requirements | Update the Search Functionality as per the latest client requirements. | See CR-001 (Client Ref #1) - search currently matches only on student name or roll number across Admissions, Installments, Students and Reports. | To be defined - awaiting the client's latest/updated search requirements; may supersede or extend CR-001. | High | Client to provide the specific, updated search requirements (fields to match on, scope of pages, replace vs. add to existing search). | New - Needs Clarification | Client | 2026-07-13
CR-013 | 11 | Global | Round numeric values to 2 decimal places | Display all applicable numeric values rounded to 2 decimal places. | Not yet verified against the current build - to be confirmed which fields currently show unrounded/inconsistent decimal precision (e.g. fee amounts, GST figures, totals). | Format all applicable numeric/currency values (fees, GST, totals, etc.) to consistently display rounded to 2 decimal places throughout the application. | Medium | Confirm full scope of "applicable numeric values" (currency fields only vs. all numeric fields) and rounding vs. truncation behavior. | New - Needs Clarification | Client | 2026-07-13